## Sheet1
System Name | CITU-Connect
Members:
A - | Bacarisas, John Clyde H.
B - | Ligan, Michael Andre B.
C - | Perolino, Sherween R.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Phase 1
1.1. Create Functional Requirements Document | B | 08/28/24 | 08/30/24 | Done
1.2. Create Gantt Chart | C | 08/28/24 | 09/23/24 | Done
Phase 2
2.1. Create GitHub Repository | A | 09/23/24 | 09/23/24 | Done
2.2. Commit FRD and Gantt Chart | A | 09/23/24 | 09/23/24 | Done
Phase 3
3.1. Assign Functionalities | A | 09/23/24 | 09/23/24 | Done
3.2. Create ERD using Visual Paradigm | A | 09/23/24 | 09/23/24 | Done
3.3. Commit ERD | A | 09/23/24 | 09/23/24 | Done
Functional Requirements Implementation
User Interface and ERD (1st Checkpoint)
1. Figma Designing |  | 2024-10-10 | 10/14/24 | Done
A. Anonymous Complaint Submission, Priority Levels, Category Tagging | A | 2024-10-10 | 10/14/24 | Done
B. Search and Filter, User Interface Dashboard, Complaint Archive | B | 2024-10-10 | 10/14/24 | Done
C. Admin Review and Approval (CRUD Operations), User Interaction, Notification System | C | 2024-10-10 | 10/14/24 | Done
2. Wireframe Prototyping |  | 10/14/24 | 10/16/24 | Done
Features Basic CRUD (2nd Checkpoint)
A. Posting Feature, Anonymous Complaint Submission, Priority Levels | A | 2024-10-30 | 2024-11-03 | Done
B. Complaint Archive, Category Tagging | B | 2024-10-30 | 2024-11-03 | Done
C. User Interaction, Notification System | C | 2024-10-30 | 2024-11-03 | Done
Improved UI (3rd Checkpoint)
A. Improved Homepage UI | A | 2024-11-05 | 2024-11-18 | Done
B. Improved Comment UI, Login UI, | B | 2024-11-05 | 2024-11-18 | Done
C. Improved Homepage UI, Landing Page UI | C | 2024-11-05 | 2024-11-18 | Done
Final Presentation
1. Create Custom Admin Page |  | 2024-11-22 | 2024-12-08 | Done
1.1 Fetch Posts wating for reviewing | A | 2024-11-23 | 2024-11-28 | Done
1.2 Add admin sidebar | A | 2024-11-24 | 2024-11-28 | Done
1.3 Post approval functionality | A | 2024-12-02 | 2024-12-08 | Done
1.4 Post rejection functionality | A | 2024-12-03 | 2024-12-09 | Done
1.5 Finalize Design | A | 2024-12-04 | 2024-12-10 | Done
2 Finalize Comment Feature | B | 2024-12-05 | 2024-12-11 | Done
3. Finalize Profile Feature | B | 2024-12-06 | 2024-12-12 | Done
4. Finalize Post Feature | A | 2024-12-07 | 2024-12-13 | Done
5. Finalize Like Dislike Feature | C | 2024-12-08 | 2024-12-14 | Done
6. Finalize Notifications Feature | C | 2024-12-09 | 2024-12-15 | Done
7. Final Touches (Animations) | B | 2024-12-10 | 2024-12-16 | Done

## Sheet2
System Name | CITU-Connect
Members:
A - | Bacarisas, John Clyde H.
B - | Ligan, Michael Andre B.
C - | Perolino, Sherween R.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1
1.1. Create